## Executive_Status
Seq | Area | Path / API / Job / UI | Current Status | Proof Seen | Blocker | Why It Matters | Owner | Next Action | Priority | Last Verified
1 | Deploy parity | /api/deploy/info | PASS | e44fb454bde3431da479bb4ecf48b094e49ae69d |  | Exact-head truth anchor | Agent-A | Keep main==serving | P0 | 2026-08-27T08:17:13Z
2 | Broker auth | /api/broker/status | PASS | AUTH_OK v279 |  | Market data prerequisite | Agent-B | Monitor token expiry | P0 | 2026-08-27T08:17:13Z
3 | Chain semantic smoke | Frontend Browser Runtime Smoke | FAIL | run 32271249820 | FINNIFTY/MIDCPNIFTY 0 at capture | Blocks CI green on exact head | Agent-C | Fix backend warm asymmetry | P0 | 2026-08-27T08:17:13Z
4 | Chain API now | /api/batch/chains | PARTIAL | 4/4 contracts populated | smoke/UI parity unproven fresh | API vs UI can diverge during warm | Agent-C | Fresh browser proof 4/4 | P0 | 2026-08-27T08:17:13Z
5 | Proof gates | /api/auto_gates | PARTIAL | None/None pass | 5 gates failing | LIVE/analyzer readiness | Agent-G | Address BLK-003 first | P1 | 2026-08-27T08:17:13Z
6 | Local repo drift | git workspace | DRIFT | 146eb69b697f86559d50519f8eaee3c8fbb8a82c | local != main | Multi-agent conflict risk | Agent-D | Rebase/sync to main | P1 | 2026-08-27T08:17:13Z
7 | Coordination artifact | resume_state.json | STALE | serving_sha old | misleading next_id | Wrong auto-resume pointer | Agent-D | Refresh after scan | P1 | 2026-08-27T08:17:13Z
8 | Agent status API | /api/agent/status | PARTIAL | has_plan=false | no owner/wave surfaced | Multi-AI coordination gap | Agent-I | Wire memory/plan contract | P2 | 2026-08-27T08:17:13Z

## Dependency_Checklist
Seq | Dependency | Code Path | Infra Resource | API Endpoint | UI Surface | Expected State | Actual State | Status | Proof | Blocker | Root Cause | Risk | Owner | Safe Next Step | Success Criteria | Failure Criteria | Rollback | Last Verified
1 | Coordination / ownership / rollback | Issue #188 / agent_policy.yaml |  |  |  | SYSTEM3_COORDINATION_V1 current owner+wave | Cloud Run revision NOT captured in scan | NOT_PROVEN |  | need gcloud describe revision | need gcloud describe revision | LOW | Agent-A | Targeted probe or fix per agent lane | SYSTEM3_COORDINATION_V1 current owner+wave | Contradictory proof or gate fail | Revert to prior serving revision | 2026-08-27T08:17:13Z
2 | main SHA / serving SHA / revision parity | /api/deploy/info |  | /api/deploy/info |  | main SHA == serving SHA | main=e44fb454bde3431da479bb4ecf48b094e49ae69d serving=e44fb454bde3431da479bb4ecf48b094e49ae69d | PASS | API deploy/info 2026-08-27T08:17:13Z |  |  | LOW | Agent-A | Targeted probe or fix per agent lane | main SHA == serving SHA | Contradictory proof or gate fail | Revert to prior serving revision | 2026-08-27T08:17:13Z
3 | PR overlap / changed-file conflicts | GitHub open PRs |  |  |  | No conflicting active PR on chain/auth lanes | open_prs=64 | PARTIAL | gh pr list 2026-08-27T08:17:13Z | review overlap manually | review overlap manually | MED | Agent-A | Targeted probe or fix per agent lane | No conflicting active PR on chain/auth lanes | Contradictory proof or gate fail | Revert to prior serving revision | 2026-08-27T08:17:13Z
4 | #294 behavior and regression execution | scripts/gcp_dhan_token_rotation_job.py |  |  |  | 906/805 excluded from rotation auth markers | PR #294 merged; 906/805 non-auth in cloud_runtime_patch | PASS | github main e44fb454bde3431da479bb4ecf48b094e49ae69d + code path |  |  | LOW | Agent-B | Targeted probe or fix per agent lane | 906/805 excluded from rotation auth markers | Contradictory proof or gate fail | Revert to prior serving revision | 2026-08-27T08:17:13Z
5 | 906 classification | core/brokers/dhan/cloud_runtime_patch.py |  |  |  | DH-906 non-auth rate-limit class | PR #294 merged; 906/805 non-auth in cloud_runtime_patch | PASS | github main e44fb454bde3431da479bb4ecf48b094e49ae69d + code path |  |  | LOW | Agent-B | Targeted probe or fix per agent lane | DH-906 non-auth rate-limit class | Contradictory proof or gate fail | Revert to prior serving revision | 2026-08-27T08:17:13Z
6 | 805 classification | core/brokers/dhan/cloud_runtime_patch.py |  |  |  | 805 non-auth too-many-requests class | PR #294 merged; 906/805 non-auth in cloud_runtime_patch | PASS | github main e44fb454bde3431da479bb4ecf48b094e49ae69d + code path |  |  | LOW | Agent-B | Targeted probe or fix per agent lane | 805 non-auth too-many-requests class | Contradictory proof or gate fail | Revert to prior serving revision | 2026-08-27T08:17:13Z
7 | genuine invalid-auth classification | /api/broker/status |  | /api/broker/status |  | AUTH_OK when token valid | connected=True auth=AUTH_OK v=321 | PASS | /api/broker/status 2026-08-27T08:17:13Z |  |  | LOW | Agent-B | Targeted probe or fix per agent lane | AUTH_OK when token valid | Contradictory proof or gate fail | Revert to prior serving revision | 2026-08-27T08:17:13Z
8 | self-heal disabled path behavior | core/engine/system3_auto_heal_orchestrator.py |  |  |  | No auth rotation on 906/805 | code excludes 906/805 from auth rotation | PARTIAL | cloud_runtime_patch.py | runtime path not re-proven | runtime path not re-proven | MED | Agent-B | Targeted probe or fix per agent lane | No auth rotation on 906/805 | Contradictory proof or gate fail | Revert to prior serving revision | 2026-08-27T08:17:13Z
9 | scheduler/manual recovery truth | genesis-system3-dhan-token-rotate job |  |  |  | Scheduled recovery bounded; no secret leak | rotation job 403 resilience NOT revalidated | NOT_PROVEN |  | inspect job logs | inspect job logs | LOW | Agent-B | Targeted probe or fix per agent lane | Scheduled recovery bounded; no secret leak | Contradictory proof or gate fail | Revert to prior serving revision | 2026-08-27T08:17:13Z
10 | IAM architecture consistency | GCP IAM / WIF |  |  |  | Keyless WIF; rotation SA least privilege | NOT scanned this run (no gcloud auth) | NOT_PROVEN |  | run gcp_runtime_iam_preflight | run gcp_runtime_iam_preflight | LOW | Agent-A | Targeted probe or fix per agent lane | Keyless WIF; rotation SA least privilege | Contradictory proof or gate fail | Revert to prior serving revision | 2026-08-27T08:17:13Z
11 | broker auth/session | /api/broker/status |  | /api/broker/status |  | connected=true credentials present | connected=True auth=AUTH_OK v=321 | PASS | /api/broker/status 2026-08-27T08:17:13Z |  |  | LOW | Agent-B | Targeted probe or fix per agent lane | connected=true credentials present | Contradictory proof or gate fail | Revert to prior serving revision | 2026-08-27T08:17:13Z
12 | broker usability beyond connected=true | market-data probes |  |  |  | Feeds usable not just profile probe | NOT_PROVEN this scan pass | NOT_PROVEN | 2026-08-27T08:17:13Z | needs targeted probe | needs targeted probe | LOW | Agent-C | Targeted probe or fix per agent lane | Feeds usable not just profile probe | Contradictory proof or gate fail | Revert to prior serving revision | 2026-08-27T08:17:13Z
13 | market-feed contract | dashboard/backend/app.py |  |  |  | Dhan-only authoritative feed contract | NOT_PROVEN this scan pass | NOT_PROVEN | 2026-08-27T08:17:13Z | needs targeted probe | needs targeted probe | LOW | Agent-C | Targeted probe or fix per agent lane | Dhan-only authoritative feed contract | Contradictory proof or gate fail | Revert to prior serving revision | 2026-08-27T08:17:13Z
14 | quote freshness | /api/live_board |  | /api/live_board |  | Fresh quotes when market open | NOT_PROVEN this scan pass | NOT_PROVEN | 2026-08-27T08:17:13Z | needs targeted probe | needs targeted probe | LOW | Agent-C | Targeted probe or fix per agent lane | Fresh quotes when market open | Contradictory proof or gate fail | Revert to prior serving revision | 2026-08-27T08:17:13Z
15 | OHLC freshness | Dhan OHLC endpoints |  |  |  | No stale/429-dominated OHLC | NOT_PROVEN this scan pass | NOT_PROVEN | 2026-08-27T08:17:13Z | needs targeted probe | needs targeted probe | LOW | Agent-C | Targeted probe or fix per agent lane | No stale/429-dominated OHLC | Contradictory proof or gate fail | Revert to prior serving revision | 2026-08-27T08:17:13Z
16 | LTP freshness | chain/index LTP paths |  |  |  | Required indices LTP live or honest closed snapshot | NOT_PROVEN this scan pass | NOT_PROVEN | 2026-08-27T08:17:13Z | needs targeted probe | needs targeted probe | LOW | Agent-C | Targeted probe or fix per agent lane | Required indices LTP live or honest closed snapshot | Contradictory proof or gate fail | Revert to prior serving revision | 2026-08-27T08:17:13Z
17 | WebSocket health | WS tick pipeline |  |  |  | WEBSOCKET_TICK_HEALTH_PROVEN gate pass | gate_pass=False | FAIL | /api/auto_gates 2026-08-27T08:17:13Z | TICK_HEALTH_BLOCKER | TICK_HEALTH_BLOCKER | HIGH | Agent-C | Targeted probe or fix per agent lane | WEBSOCKET_TICK_HEALTH_PROVEN gate pass | Contradictory proof or gate fail | Revert to prior serving revision | 2026-08-27T08:17:13Z
18 | cache fallback detection | batch_chains / push cache |  |  |  | Fallback labeled; no silent synthetic prices | NOT_PROVEN this scan pass | NOT_PROVEN | 2026-08-27T08:17:13Z | needs targeted probe | needs targeted probe | LOW | Agent-C | Targeted probe or fix per agent lane | Fallback labeled; no silent synthetic prices | Contradictory proof or gate fail | Revert to prior serving revision | 2026-08-27T08:17:13Z
19 | rate-limit detection | 805/429 handlers |  |  |  | Rate limits surfaced not misclassified auth | [] | NOT_PROVEN | smoke394 manifest | 805 seen in smoke session | 805 seen in smoke session | LOW | Agent-C | Targeted probe or fix per agent lane | Rate limits surfaced not misclassified auth | Contradictory proof or gate fail | Revert to prior serving revision | 2026-08-27T08:17:13Z
20 | NIFTY chain freshness | /api/batch/chains NIFTY |  | /api/batch/chains NIFTY |  | contracts>0 semantic source | api_contracts=462 smoke_contracts=None | PARTIAL | /api/batch/chains + smoke394 None | warm race / semantic source incomplete | warm race / semantic source incomplete | MED | Agent-C | Targeted probe or fix per agent lane | contracts>0 semantic source | Contradictory proof or gate fail | Revert to prior serving revision | 2026-08-27T08:17:13Z
21 | BANKNIFTY chain freshness | /api/batch/chains BANKNIFTY |  | /api/batch/chains BANKNIFTY |  | contracts>0 semantic source | api_contracts=462 smoke_contracts=None | PARTIAL | /api/batch/chains + smoke394 None | warm race / semantic source incomplete | warm race / semantic source incomplete | MED | Agent-C | Targeted probe or fix per agent lane | contracts>0 semantic source | Contradictory proof or gate fail | Revert to prior serving revision | 2026-08-27T08:17:13Z
22 | FINNIFTY chain freshness | /api/batch/chains FINNIFTY |  | /api/batch/chains FINNIFTY |  | contracts>0; no warm race at smoke capture | api_contracts=462 smoke_contracts=None | PARTIAL | /api/batch/chains + smoke394 None | warm race / semantic source incomplete | warm race / semantic source incomplete | MED | Agent-C | Targeted probe or fix per agent lane | contracts>0; no warm race at smoke capture | Contradictory proof or gate fail | Revert to prior serving revision | 2026-08-27T08:17:13Z
23 | MIDCPNIFTY chain freshness | /api/batch/chains MIDCPNIFTY |  | /api/batch/chains MIDCPNIFTY |  | contracts>0; no warm race at smoke capture | api_contracts=462 smoke_contracts=None | PARTIAL | /api/batch/chains + smoke394 None | warm race / semantic source incomplete | warm race / semantic source incomplete | MED | Agent-C | Targeted probe or fix per agent lane | contracts>0; no warm race at smoke capture | Contradictory proof or gate fail | Revert to prior serving revision | 2026-08-27T08:17:13Z
24 | universe/API/UI parity | universe CSV + UI tabs |  |  |  | Same symbol set across API and UI | NOT_PROVEN this scan pass | NOT_PROVEN | 2026-08-27T08:17:13Z | needs targeted probe | needs targeted probe | LOW | Agent-C | Targeted probe or fix per agent lane | Same symbol set across API and UI | Contradictory proof or gate fail | Revert to prior serving revision | 2026-08-27T08:17:13Z
25 | waiting/loading/blank semantic truth | 22 UI tabs |  |  |  | Honest WAITING/LOADING not fake PASS | tabs_with_wait=0 | PARTIAL | smoke394 | honest waiting states present | honest waiting states present | MED | Agent-I | Targeted probe or fix per agent lane | Honest WAITING/LOADING not fake PASS | Contradictory proof or gate fail | Revert to prior serving revision | 2026-08-27T08:17:13Z
26 | verified option contracts | OptionChain UI + chain API |  |  |  | Verified broker rows visible | gate_pass=False blocker=None | FAIL | /api/auto_gates 2026-08-27T08:17:13Z | SYS3-BLK-003 | SYS3-BLK-003 | HIGH | Agent-C | Targeted probe or fix per agent lane | Verified broker rows visible | Contradictory proof or gate fail | Revert to prior serving revision | 2026-08-27T08:17:13Z
27 | data foundation coverage | data foundation services |  |  |  | Coverage metrics current | NOT_PROVEN this scan pass | NOT_PROVEN | 2026-08-27T08:17:13Z | needs targeted probe | needs targeted probe | LOW | Agent-E | Targeted probe or fix per agent lane | Coverage metrics current | Contradictory proof or gate fail | Revert to prior serving revision | 2026-08-27T08:17:13Z
28 | 1-year historical data availability | historical store |  |  |  | >=1y for core symbols | NOT_PROVEN this scan pass | NOT_PROVEN | 2026-08-27T08:17:13Z | needs targeted probe | needs targeted probe | LOW | Agent-E | Targeted probe or fix per agent lane | >=1y for core symbols | Contradictory proof or gate fail | Revert to prior serving revision | 2026-08-27T08:17:13Z
29 | historical backfill automation | backfill jobs |  |  |  | Idempotent scheduled backfill | NOT_PROVEN this scan pass | NOT_PROVEN | 2026-08-27T08:17:13Z | needs targeted probe | needs targeted probe | LOW | Agent-E | Targeted probe or fix per agent lane | Idempotent scheduled backfill | Contradictory proof or gate fail | Revert to prior serving revision | 2026-08-27T08:17:13Z
30 | feature snapshot pipeline | feature snapshot jobs |  |  |  | Fresh feature snapshots | NOT_PROVEN this scan pass | NOT_PROVEN | 2026-08-27T08:17:13Z | needs targeted probe | needs targeted probe | LOW | Agent-F | Targeted probe or fix per agent lane | Fresh feature snapshots | Contradictory proof or gate fail | Revert to prior serving revision | 2026-08-27T08:17:13Z
31 | prediction source existence | prediction pipeline |  |  |  | Active prediction source configured | NOT_PROVEN this scan pass | NOT_PROVEN | 2026-08-27T08:17:13Z | needs targeted probe | needs targeted probe | LOW | Agent-F | Targeted probe or fix per agent lane | Active prediction source configured | Contradictory proof or gate fail | Revert to prior serving revision | 2026-08-27T08:17:13Z
32 | prediction logging | prediction store |  |  |  | Row-level prediction_id logging | NOT_PROVEN this scan pass | NOT_PROVEN | 2026-08-27T08:17:13Z | needs targeted probe | needs targeted probe | LOW | Agent-F | Targeted probe or fix per agent lane | Row-level prediction_id logging | Contradictory proof or gate fail | Revert to prior serving revision | 2026-08-27T08:17:13Z
33 | matured outcome labeling | outcome labeling jobs |  |  |  | Matured labels for horizons | NOT_PROVEN this scan pass | NOT_PROVEN | 2026-08-27T08:17:13Z | needs targeted probe | needs targeted probe | LOW | Agent-F | Targeted probe or fix per agent lane | Matured labels for horizons | Contradictory proof or gate fail | Revert to prior serving revision | 2026-08-27T08:17:13Z
34 | post-market validation | daily_gain_validate |  |  |  | Weekday validation job runs | NOT_PROVEN this scan pass | NOT_PROVEN | 2026-08-27T08:17:13Z | needs targeted probe | needs targeted probe | LOW | Agent-F | Targeted probe or fix per agent lane | Weekday validation job runs | Contradictory proof or gate fail | Revert to prior serving revision | 2026-08-27T08:17:13Z
35 | canonical accuracy report | /api/accuracy_trend |  | /api/accuracy_trend |  | Report present and gate-aligned | gate_pass=True | PASS | /api/auto_gates 2026-08-27T08:17:13Z |  |  | LOW | Agent-F | Targeted probe or fix per agent lane | Report present and gate-aligned | Contradictory proof or gate fail | Revert to prior serving revision | 2026-08-27T08:17:13Z
36 | leakage guard | tests/evals leakage specs |  |  |  | No leakage in promotion path | NOT_PROVEN this scan pass | NOT_PROVEN | 2026-08-27T08:17:13Z | needs targeted probe | needs targeted probe | LOW | Agent-G | Targeted probe or fix per agent lane | No leakage in promotion path | Contradictory proof or gate fail | Revert to prior serving revision | 2026-08-27T08:17:13Z
37 | timestamp alignment | feature/label timestamps |  |  |  | PIT-safe alignment | NOT_PROVEN this scan pass | NOT_PROVEN | 2026-08-27T08:17:13Z | needs targeted probe | needs targeted probe | LOW | Agent-G | Targeted probe or fix per agent lane | PIT-safe alignment | Contradictory proof or gate fail | Revert to prior serving revision | 2026-08-27T08:17:13Z
38 | model registry/provenance | model registry |  |  |  | Versioned model lineage | NOT_PROVEN this scan pass | NOT_PROVEN | 2026-08-27T08:17:13Z | needs targeted probe | needs targeted probe | LOW | Agent-G | Targeted probe or fix per agent lane | Versioned model lineage | Contradictory proof or gate fail | Revert to prior serving revision | 2026-08-27T08:17:13Z
39 | heuristic vs ML truth labeling | ML tab / gates |  |  |  | Honest heuristic vs ML labels | NOT_PROVEN this scan pass | NOT_PROVEN | 2026-08-27T08:17:13Z | needs targeted probe | needs targeted probe | LOW | Agent-G | Targeted probe or fix per agent lane | Honest heuristic vs ML labels | Contradictory proof or gate fail | Revert to prior serving revision | 2026-08-27T08:17:13Z
40 | ML blocker truthfulness | /api/auto_gates ML gate |  | /api/auto_gates ML gate |  | rho gate reflects real evidence | gate_pass=False blocker=None | FAIL | /api/auto_gates 2026-08-27T08:17:13Z |  |  | HIGH | Agent-G | Targeted probe or fix per agent lane | rho gate reflects real evidence | Contradictory proof or gate fail | Revert to prior serving revision | 2026-08-27T08:17:13Z
41 | backtest proof validity | backtest artifacts |  |  |  | Costs/leakage-safe backtests | NOT_PROVEN this scan pass | NOT_PROVEN | 2026-08-27T08:17:13Z | needs targeted probe | needs targeted probe | LOW | Agent-G | Targeted probe or fix per agent lane | Costs/leakage-safe backtests | Contradictory proof or gate fail | Revert to prior serving revision | 2026-08-27T08:17:13Z
42 | paper lifecycle | paper tab / paper engine |  |  |  | REAL_PAPER_LIFECYCLE gate pass | gate_pass=False | FAIL | /api/auto_gates 2026-08-27T08:17:13Z |  |  | HIGH | Agent-H | Targeted probe or fix per agent lane | REAL_PAPER_LIFECYCLE gate pass | Contradictory proof or gate fail | Revert to prior serving revision | 2026-08-27T08:17:13Z
43 | closed-trade reconciliation | paper recon QC |  |  |  | Closed trades reconciled | NOT_PROVEN this scan pass | NOT_PROVEN | 2026-08-27T08:17:13Z | needs targeted probe | needs targeted probe | LOW | Agent-H | Targeted probe or fix per agent lane | Closed trades reconciled | Contradictory proof or gate fail | Revert to prior serving revision | 2026-08-27T08:17:13Z
44 | QC readiness | /api/health qc_status |  | /api/health qc_status |  | QC PASS with evidence | qc_status=NOT_READY | PARTIAL | /api/health 2026-08-27T08:17:13Z |  |  | MED | Agent-H | Targeted probe or fix per agent lane | QC PASS with evidence | Contradictory proof or gate fail | Revert to prior serving revision | 2026-08-27T08:17:13Z
45 | compliance/proof-pack parity | e2e-proof tab |  |  |  | Proof pack matches runtime | e2e-proof WAITING · 4 CHAINS in smoke394 | PARTIAL | smoke394 semantic_attention | chains incomplete at smoke capture | chains incomplete at smoke capture | MED | Agent-H | Targeted probe or fix per agent lane | Proof pack matches runtime | Contradictory proof or gate fail | Revert to prior serving revision | 2026-08-27T08:17:13Z
46 | /api/agent/status truthfulness | /api/agent/status |  | /api/agent/status |  | memory/plan/owner/wave truthful | has_memory=False has_plan=False | PARTIAL | /api/agent/status 2026-08-27T08:17:13Z | coordination fields incomplete | coordination fields incomplete | MED | Agent-I | Targeted probe or fix per agent lane | memory/plan/owner/wave truthful | Contradictory proof or gate fail | Revert to prior serving revision | 2026-08-27T08:17:13Z
47 | current owner/wave/next dependency | resume_state + Issue #188 |  |  |  | Matches live scan next action | resume_serving_sha=None live=e44fb454bde3431da479bb4ecf48b094e49ae69d | STALE | resume_state.json + deploy/info | resume_state stale vs production | resume_state stale vs production | HIGH | Agent-I | Targeted probe or fix per agent lane | Matches live scan next action | Contradictory proof or gate fail | Revert to prior serving revision | 2026-08-27T08:17:13Z
48 | final rollback readiness | deploy/info + Cloud Run revisions |  |  |  | Known rollback target revision | Cloud Run revision NOT captured in scan | NOT_PROVEN |  | need gcloud describe revision | need gcloud describe revision | LOW | Agent-A | Targeted probe or fix per agent lane | Known rollback target revision | Contradictory proof or gate fail | Revert to prior serving revision | 2026-08-27T08:17:13Z

## Task_Breakdown
Task ID | Parent Dependency | Assigned Agent | Scope | Allowed Files/Resources | Blocked Files/Resources | Preconditions | Action | Deliverable | Status | Proof Required | Success Criteria | Failure Criteria | ETA | Notes
T-C1 | Chain warm asymmetry | Agent-C | Backend chain cache warm/fanout | dashboard/backend/app.py; tests/evals/ | rotation secrets; IAM | main==serving; broker AUTH_OK | Patch batch_chains warm path | PR + eval pass | IMPLEMENTED_PENDING_LIVE_SMOKE | smoke 4/4 + API summary | FINNIFTY/MIDCPNIFTY ready at capture | Still 0 contracts at smoke | 1-2d | PCR/UI mismatch deferred
T-A1 | Scan runner maintenance | Agent-D | MRI scan + workbook refresh | scripts/system3_master_mri_*; reports/latest/master_mri/ | production mutations | scan runner exists | Re-run after each merge | latest_scan.json + xlsx | IN_PROGRESS | timestamped JSON | diff rows updated | stale workbook | ongoing
T-A2 | Resume state refresh | Agent-D | continuous_closure resume | reports/latest/continuous_closure/ | gate thresholds | post-deploy SHA known | Update serving_sha + gates | resume_state.json | PENDING | matches deploy/info | pointer matches live | stale next_id | same day
T-B1 | Rotation job IAM 403 | Agent-B | Cloud Run job invoke IAM | GCP IAM docs; job yaml | secret payloads | user approval for IAM | Repair invoker binding | job execute success | BLOCKED | job run log | 403 cleared | still 403 | TBD | USER_ACTION for IAM
T-I1 | Agent status contract | Agent-I | /api/agent/status owner/wave | dashboard/backend agent routes | LIVE flags | coordination schema agreed | Expose has_plan/memory truth | API fields populated | PENDING | agent/status JSON | owner/wave visible | false READY | 2d

## Proof_Register
Proof ID | Dependency | Proof Type | Source | Exact Path/URL/API/Log | Timestamp | Verified By | Result | Notes
P-001 | main/serving parity | API | production | /api/deploy/info | 2026-08-27T08:17:13Z | MRI scan | PASS | e44fb454bde3431da479bb4ecf48b094e49ae69d
P-002 | broker auth | API | production | /api/broker/status | 2026-08-27T08:17:13Z | MRI scan | PASS | v279 AUTH_OK
P-003 | chain API | API | production | /api/batch/chains | 2026-08-27T08:17:13Z | MRI scan | PARTIAL | 4/4 contracts; smoke failed
P-004 | smoke CI | CI | GitHub Actions | run/32271249820 | 2026-08-19T15:44:27Z | MRI scan | FAIL | .artifacts/smoke394
P-005 | auto gates | API | production | /api/auto_gates | 2026-08-27T08:17:13Z | MRI scan | PARTIAL | None/None
P-006 | local git | LOCAL | workspace | git rev-parse HEAD | 2026-08-27T08:17:13Z | MRI scan | DRIFT | 146eb69b697f86559d50519f8eaee3c8fbb8a82c

## Sequence_Plan
Step | Dependency | Why First | Preconditions | Assigned Agent | Safe Action | Success Proof | Do Not Do | Status
1 | MRI scan layer | Establishes diff truth before coding | none | Agent-D | Run scan runner + workbook | latest_scan.json | Skip fresh evidence | DONE
2 | Chain warm backend | Exact-head smoke FAIL root boundary | broker AUTH_OK | Agent-C | Patch app.py warm/fanout | smoke 4/4 PASS | Cosmetic UI green | IMPLEMENTED_PENDING_LIVE_SMOKE
3 | Fresh browser proof | UI is final truth surface | backend patch deployed | Agent-C | gcp_live_ui_snapshot.py | semantic chain proof | Trust API alone | PENDING
4 | Resume/coordination refresh | Prevent wrong auto-resume | serving SHA stable | Agent-D | Update resume_state + #188 | workbook row match | Stale reports as truth | PENDING
5 | Full cloud audit re-eval | May be downstream of chain | smoke pass | Agent-A | Re-run workflow | consensus pass | Assume old fail cause | PENDING

## PR_and_Ownership
Issue/PR | Branch | Owner | Scope | Files Changed | Conflict Risk | Allowed To Edit | Notes
#377 | feat/data-lake-ingestion-376 | UNASSIGNED | feat(data-lake): scaffold GCS ingestion/storage module | NOT_PROVEN | LOW | PR author | 2026-08-27T07:52:43Z
#353 | docs/ruhi-user-reference-20260824 | UNASSIGNED | docs(ruhi): publish user recommendation reference pack | NOT_PROVEN | LOW | PR author | 2026-08-26T19:26:10Z
#348 | feat/github-control-monitor-20260824 | UNASSIGNED | feat(control-plane): add GitHub closure monitor ledger | NOT_PROVEN | LOW | PR author | 2026-08-24T15:21:54Z
#336 | docs/perplexity-independent-forensic-controller-20260824 | UNASSIGNED | docs(coordination): add Perplexity independent forensic controller handoff | NOT_PROVEN | LOW | PR author | 2026-08-25T14:02:02Z
#335 | chatgpt/same-document-ui-semantic-proof-20260824 | UNASSIGNED | test(ui): preserve one hydrated document across semantic tab proof | NOT_PROVEN | LOW | PR author | 2026-08-24T12:03:23Z
#324 | docs/catalyst-early-warning-plan-20260822 | UNASSIGNED | docs(catalyst): add Catalyst Early Warning Intelligence implementation authority | NOT_PROVEN | LOW | PR author | 2026-08-22T11:42:27Z
#323 | cursor/ui-closure-rule-2b45 | UNASSIGNED | docs(ruhi): lock Cursor permanent UI-closure rule | NOT_PROVEN | LOW | PR author | 2026-08-22T11:01:51Z
#317 | docs/cursor-coordination-contract-20260822 | UNASSIGNED | docs(cursor): enforce multi-agent coordination and proof contract | NOT_PROVEN | LOW | PR author | 2026-08-22T13:34:51Z
#315 | docs/central-agent-coordination-20260822 | UNASSIGNED | docs: add permanent central multi-agent coordination ledger | NOT_PROVEN | LOW | PR author | 2026-08-22T00:54:38Z
#314 | cursor/cloud-agent-env-setup-9d91 | UNASSIGNED | chore(env): Cloud Agent dev environment setup for the System3 dashboard | NOT_PROVEN | LOW | PR author | 2026-08-22T00:05:51Z
#304 | docs/codex-ruhi-execution | UNASSIGNED | docs: add Codex CLI RUHI execution guide | NOT_PROVEN | LOW | PR author | 2026-08-21T08:48:27Z
#291 | feat/repo-clean-forensic-toolkit-v1-2-actions-storage-20260819 | UNASSIGNED | feat(cleanup): exact-digest GitHub Actions storage evidence | NOT_PROVEN | LOW | PR author | 2026-08-18T22:11:58Z
#286 | fix/20260819-scheduler-health-verifier-diagnostics | UNASSIGNED | test(control-plane): add fail-closed scheduler-health diagnostic gate | NOT_PROVEN | LOW | PR author | 2026-08-19T04:28:05Z
#279 | docs/chatgpt-current-handoff-20260818 | UNASSIGNED | docs(chatgpt): current live handoff + Cursor instruction slot | NOT_PROVEN | LOW | PR author | 2026-08-18T05:01:01Z
#261 | dependabot/github_actions/actions/upload-artifact-7 | UNASSIGNED | chore(deps): bump actions/upload-artifact from 4 to 7 | NOT_PROVEN | LOW | PR author | 2026-08-26T18:49:23Z
#242 | audit/cursor-full-cloud-ui-forensic-20260816T062501Z | UNASSIGNED | docs(audit): full cloud+UI forensic package 20260816T062501Z | NOT_PROVEN | LOW | PR author | 2026-08-16T08:06:09Z
#217 | fix/dependabot-vite-safe-major | UNASSIGNED | security: keep Vite Dependabot updates on compatible remediation major | NOT_PROVEN | LOW | PR author | 2026-08-14T17:36:59Z
#215 | dependabot/pip/statsmodels-gte-0.14.6 | UNASSIGNED | build(deps): update statsmodels requirement from >=0.14.2 to >=0.14.6 | NOT_PROVEN | LOW | PR author | 2026-08-14T17:20:41Z
#214 | dependabot/pip/pyotp-2.10.0 | UNASSIGNED | build(deps): bump pyotp from 2.9.0 to 2.10.0 | NOT_PROVEN | LOW | PR author | 2026-08-14T17:20:37Z
#213 | dependabot/pip/yamllint-1.38.0 | UNASSIGNED | build(deps): bump yamllint from 1.35.1 to 1.38.0 | NOT_PROVEN | LOW | PR author | 2026-08-14T17:20:33Z
#212 | dependabot/pip/jugaad-data-gte-0.35.2 | UNASSIGNED | build(deps): update jugaad-data requirement from >=0.31.1 to >=0.35.2 | NOT_PROVEN | LOW | PR author | 2026-08-14T17:15:44Z
#211 | dependabot/pip/yfinance-gte-1.5.2 | UNASSIGNED | build(deps): update yfinance requirement from >=0.2.38 to >=1.5.2 | NOT_PROVEN | LOW | PR author | 2026-08-14T17:14:54Z
#209 | dependabot/github_actions/SonarSource/sonarqube-scan-action-8 | UNASSIGNED | chore(deps): bump SonarSource/sonarqube-scan-action from 7 to 8 | NOT_PROVEN | LOW | PR author | 2026-08-26T18:49:34Z
#208 | dependabot/github_actions/actions/setup-python-7 | UNASSIGNED | chore(deps): bump actions/setup-python from 5 to 7 | NOT_PROVEN | LOW | PR author | 2026-08-26T18:50:25Z
#207 | dependabot/pip/dashboard/backend/numpy-2.5.2 | UNASSIGNED | build(deps): bump numpy from 2.2.6 to 2.5.2 in /dashboard/backend | NOT_PROVEN | LOW | PR author | 2026-08-14T16:49:12Z
#206 | dependabot/pip/dashboard/backend/uvicorn-0.52.1 | UNASSIGNED | build(deps): bump uvicorn from 0.49.0 to 0.52.1 in /dashboard/backend | NOT_PROVEN | LOW | PR author | 2026-08-14T16:49:06Z
#205 | dependabot/pip/dashboard/backend/google-cloud-secret-manager-gte-2.30.0-and-lt-3.0.0 | UNASSIGNED | build(deps): update google-cloud-secret-manager requirement from <3.0.0,>=2.20.0 to >=2.30.0,<3.0.0 in /dashboard/backend | NOT_PROVEN | LOW | PR author | 2026-08-14T16:49:01Z
#203 | dependabot/npm_and_yarn/dashboard/frontend/recharts-3.10.1 | UNASSIGNED | build(deps): bump recharts from 2.15.4 to 3.10.1 in /dashboard/frontend | NOT_PROVEN | LOW | PR author | 2026-08-14T16:48:32Z
#202 | dependabot/npm_and_yarn/dashboard/frontend/tailwind-merge-3.6.0 | UNASSIGNED | build(deps): bump tailwind-merge from 2.6.1 to 3.6.0 in /dashboard/frontend | NOT_PROVEN | LOW | PR author | 2026-08-14T16:48:24Z
#201 | dependabot/npm_and_yarn/dashboard/frontend/lucide-react-1.31.0 | UNASSIGNED | build(deps): bump lucide-react from 0.294.0 to 1.31.0 in /dashboard/frontend | NOT_PROVEN | LOW | PR author | 2026-08-14T16:48:19Z
#200 | dependabot/npm_and_yarn/dashboard/frontend/typescript-7.0.2 | UNASSIGNED | chore(deps-dev): bump typescript from 5.9.3 to 7.0.2 in /dashboard/frontend | NOT_PROVEN | LOW | PR author | 2026-08-16T15:36:55Z
#199 | dependabot/pip/dashboard/backend/pandas-3.0.5 | UNASSIGNED | build(deps): bump pandas from 2.3.3 to 3.0.5 in /dashboard/backend | NOT_PROVEN | LOW | PR author | 2026-08-14T16:48:09Z
#197 | dependabot/pip/dashboard/backend/fastapi-0.141.1 | UNASSIGNED | build(deps): bump fastapi from 0.138.0 to 0.141.1 in /dashboard/backend | NOT_PROVEN | LOW | PR author | 2026-08-14T16:48:04Z
#196 | dependabot/github_actions/actions/setup-node-7 | UNASSIGNED | chore(deps): bump actions/setup-node from 4 to 7 | NOT_PROVEN | LOW | PR author | 2026-08-26T18:49:29Z
#195 | dependabot/docker/python-3.14-slim | UNASSIGNED | build(deps): bump python from 3.10-slim to 3.14-slim | NOT_PROVEN | LOW | PR author | 2026-08-14T16:48:00Z
#192 | fix/20260814-paper-url-truth-gate | UNASSIGNED | fix(paper): durable Cloud Run paper ledger + semantic URL truth gates | NOT_PROVEN | LOW | PR author | 2026-08-14T08:53:43Z
#191 | fix/ui-option-parity-proof-20260814 | UNASSIGNED | test(gcp): make production option-chain UI parity a post-deploy gate | NOT_PROVEN | MED | PR author | 2026-08-14T04:43:23Z
#189 | feat/market-data-readonly-failover-20260814 | UNASSIGNED | feat(data): read-only broker market-data failover core | NOT_PROVEN | LOW | PR author | 2026-08-14T04:01:45Z
#182 | fix/frontend-typecheck-gate-20260814 | UNASSIGNED | test(frontend): strict TypeScript gate — repair pass 2 | NOT_PROVEN | LOW | PR author | 2026-08-13T21:24:51Z
#165 | fix/ui-semantic-hydration-typecheck-20260813 | UNASSIGNED | Harden production UI semantic hydration proof | NOT_PROVEN | LOW | PR author | 2026-08-13T14:38:07Z
#139 | feat/ui-mobile-shell-review | UNASSIGNED | feat(ui): reclaim mobile workspace with compact navigation | NOT_PROVEN | LOW | PR author | 2026-08-12T08:52:28Z
#131 | fix/public-readonly-runtime-slice | UNASSIGNED | security: current-main public-readonly runtime boundary | NOT_PROVEN | LOW | PR author | 2026-08-12T07:34:47Z
#129 | fix/permanent-public-dashboard-no-key | UNASSIGNED | security: permanently remove dashboard credential and session authority | NOT_PROVEN | LOW | PR author | 2026-08-12T04:53:59Z
#125 | feat/sre-operations-truth-v1 | UNASSIGNED | feat(sre): add fail-closed OperationsTruth inventory and SLO scorecard | NOT_PROVEN | LOW | PR author | 2026-08-12T00:44:49Z
#121 | feat/gcp-observability-phase1 | UNASSIGNED | feat(observability): add traced read-only 24x7 monitoring foundation | NOT_PROVEN | LOW | PR author | 2026-08-11T23:40:13Z
#115 | fix/no-key-deploy-proof-contract-20260812 | UNASSIGNED | fix(gcp): make Cloud Run static proof command-aware | NOT_PROVEN | LOW | PR author | 2026-08-11T21:57:31Z
#110 | fix/gcp-atomic-runtime-spec-20260811 | UNASSIGNED | fix(gcp): deploy one canonical Cloud Run runtime revision | NOT_PROVEN | LOW | PR author | 2026-08-11T16:25:16Z
#98 | fix/dashboard-vcloak-css-issue-44 | UNASSIGNED | fix(dashboard): add missing [v-cloak] CSS rule to hide raw template t… | NOT_PROVEN | LOW | PR author | 2026-08-11T11:18:26Z
#97 | fix/paper-pnl-synthetic-data-guard-20260811 | UNASSIGNED | fix(dashboard): guard live P&L sync against synthetic/paper-simulatio… | NOT_PROVEN | LOW | PR author | 2026-08-10T23:55:29Z
#84 | copilot/fix-negative-holdout-issues | UNASSIGNED | Harden analyzer-only frozen evaluation and ML proof gating for unreliable holdout/UI states | NOT_PROVEN | LOW | PR author | 2026-08-10T17:12:29Z
#83 | copilot/implement-p0-stabilization-patch | UNASSIGNED | [WIP] Implement P0 stabilization patch for trading reliability and GCP migration | NOT_PROVEN | LOW | PR author | 2026-08-04T21:01:24Z
#81 | feat/nonlive-equity-options-bigdata-pipeline | UNASSIGNED | feat(research): resumable all-equity options big-data and leakage-safe backtest | NOT_PROVEN | LOW | PR author | 2026-08-05T13:30:13Z
#80 | fix-paper-console-truth-mobile | UNASSIGNED | fix(ui): paper console status and mobile layout | NOT_PROVEN | LOW | PR author | 2026-07-07T06:14:01Z
#78 | fix/core-pipeline-v8-paper-ledger | UNASSIGNED | feat(paper): add core pipeline v8 paper ledger and proof | NOT_PROVEN | LOW | PR author | 2026-07-06T18:49:42Z
#76 | copilot/verify-remediate-github-actions | UNASSIGNED | Normalize cloud runtime check output for dashboard-auth-protected endpoints | NOT_PROVEN | LOW | PR author | 2026-07-06T10:44:48Z
#67 | copilot/fix-blocking-workflow-policy-issue | UNASSIGNED | Fix blocking workflow-policy guard by restoring single-workflow layout | NOT_PROVEN | LOW | PR author | 2026-07-03T18:23:18Z
#65 | fix-render-api-502-readonly-stability | UNASSIGNED | Stabilize dashboard API polling | NOT_PROVEN | LOW | PR author | 2026-07-05T08:21:18Z
#51 | chatgpt/cloud-forensic-gates-20260701 | UNASSIGNED | docs: add cloud CI failure triage proof | NOT_PROVEN | LOW | PR author | 2026-07-01T08:54:24Z
#43 | cloud-live-ui-paper-prediction-proof | UNASSIGNED | Add corrected cloud dashboard proof workflow | NOT_PROVEN | LOW | PR author | 2026-06-24T07:18:04Z
#42 | copilot/complete-dashboard-enhancement | UNASSIGNED | [WIP] Implement all recommended features for dashboard enhancement | NOT_PROVEN | LOW | PR author | 2026-06-24T13:51:02Z
#41 | copilot/complete-trader-audit-phase-1 | UNASSIGNED | [WIP] Add comprehensive audit endpoints for trading system | NOT_PROVEN | LOW | PR author | 2026-06-23T17:17:38Z
#40 | copilot/phase-1-backend-api-expansion | UNASSIGNED | [WIP] Expand backend API for portfolio overview and details | NOT_PROVEN | LOW | PR author | 2026-06-23T17:12:30Z
#39 | copilot/full-production-readiness-audit | UNASSIGNED | [WIP] Conduct dashboard production readiness audit | NOT_PROVEN | LOW | PR author | 2026-06-23T17:06:49Z
#38 | copilot/activate-dhan-data-api | UNASSIGNED | [WIP] Activate Dhan Data API as P0 source with token safety measures | NOT_PROVEN | LOW | PR author | 2026-06-23T17:02:46Z

## Runtime_Parity
Area | Main SHA | Serving Revision | Serving SHA | URL Evidence | API Evidence | Match Status | Notes
Deploy SHA | e44fb454bde3431da479bb4ecf48b094e49ae69d | NOT_PROVEN | e44fb454bde3431da479bb4ecf48b094e49ae69d | N/A | /api/deploy/info | MATCH
Broker | e44fb454bde3431da479bb4ecf48b094e49ae69d | NOT_PROVEN | e44fb454bde3431da479bb4ecf48b094e49ae69d | broker tab historical | /api/broker/status AUTH_OK | PARTIAL | fresh UI not captured this run
Chains | e44fb454bde3431da479bb4ecf48b094e49ae69d | NOT_PROVEN | e44fb454bde3431da479bb4ecf48b094e49ae69d | smoke394 PARTIAL | /api/batch/chains 4/4 | PARTIAL | API populated; smoke failed

## Repo_Environment_Diff
Area | Local State | GitHub State | GCP State | Runtime/UI State | Match/Drift Status | Proof | Blocker | Next Action

## Market_Data_Truth
Signal Area | Source Path | Expected | Actual | Status | Proof | Freshness | Rate-Limit Risk | Fallback Risk | Next Step
NIFTY chain | /api/batch/chains | contracts>0 dhan snapshot | contracts=462 status=None | PASS | 2026-08-27T08:17:13Z | closed-market snapshot | 805 seen in smoke session | paced_chain_cache | Backend warm fix + fresh UI
BANKNIFTY chain | /api/batch/chains | contracts>0 dhan snapshot | contracts=714 status=None | PASS | 2026-08-27T08:17:13Z | closed-market snapshot | 805 seen in smoke session | paced_chain_cache | Backend warm fix + fresh UI
FINNIFTY chain | /api/batch/chains | contracts>0 dhan snapshot | contracts=478 status=None | PASS | 2026-08-27T08:17:13Z | closed-market snapshot | 805 seen in smoke session | paced_chain_cache | Backend warm fix + fresh UI
MIDCPNIFTY chain | /api/batch/chains | contracts>0 dhan snapshot | contracts=506 status=None | PASS | 2026-08-27T08:17:13Z | closed-market snapshot | 805 seen in smoke session | paced_chain_cache | Backend warm fix + fresh UI
OHLC feed | Dhan OHLC | no 429 | 805 in smoke394 | PARTIAL | smoke394 | stale at capture | HIGH | cache fallback | Rate-limit aware pacing

## ML_Data_Pipeline
Stage | Dataset / Source | Code Path / Job | Coverage | Freshness | Prediction Count | Matured Count | Status | Proof | Blocker | Next Step
Accuracy gate | Firestore evidence | daily_gain_validate | NOT_PROVEN | NOT_PROVEN | NOT_PROVEN | NOT_PROVEN | FAIL | /api/auto_gates | SYS3-BLK-005 | Run validation job
Model report | accuracy report | report pipeline | NOT_PROVEN | NOT_PROVEN | NOT_PROVEN | NOT_PROVEN | PASS | MODEL_ACCURACY_REPORT_PRESENT |  | Maintain
Feature snapshots | feature store | snapshot jobs | NOT_PROVEN | NOT_PROVEN | NOT_PROVEN | NOT_PROVEN | NOT_PROVEN |  |  | Agent-F probe

## Paper_Recon_QC
Stage | Source | Expected | Actual | Status | Proof | Blocker | Next Step | Success Criteria
Paper lifecycle gate | /api/auto_gates | REAL_PAPER_LIFECYCLE pass | FAIL | FAIL | 2026-08-27T08:17:13Z | SYS3-BLK-008 | Market-day proof | Gate pass
QC health | /api/health | qc_status PASS | PASS | PASS | 2026-08-27T08:17:13Z |  | Maintain | qc_status PASS
Paper UI | paper tab | positions loaded | LOADING in smoke394 | PARTIAL | smoke394 |  | Fresh UI capture | No perpetual LOADING

## Change_Control
Change ID | Dependency | Risk Level | Pre-Checks | Mutating? | Approval Needed | Rollback Ready | Status | Notes
CC-001 | Chain warm backend fix | MED | eval + CI | Yes code deploy | No | PARTIAL | READY | No LIVE change
CC-002 | Rotation job IAM repair | HIGH | gcloud describe | Yes IAM | Yes USER | NOT_PROVEN | BLOCKED | Break-glass
CC-003 | Workbook/scan only | LOW | read-only scan | No | No | N/A | DONE | This MRI run

## Final_Proof_Summary
Area | Code Proof | CI Proof | API Proof | URL Proof | Workbook Updated | Final Status | Remaining Gap
Deploy parity | main at PR#294 | Auto Deploy PASS | deploy/info PASS | NOT_PROVEN fresh | Yes | PASS
Broker auth | PR#294 merged | Safety CI PASS | broker/status PASS | broker tab historical | Yes | PASS | usability beyond probe
Chain semantic | NOT FIXED | Smoke FAIL | API 4/4 PARTIAL | smoke394 FAIL | Yes | FAIL | warm asymmetry + fresh UI
Proof gates | partial | audit FAIL | 2/7 pass | multiple WAITING | Yes | PARTIAL | 5 gates red
Coordination | scan runner added | preflight rate-limited | agent/status PARTIAL | N/A | Yes | PARTIAL | Issue #188 refresh